## Sheet1
Schedule "B"
THE VENDOR SHALL COMPLETE THE DEMOLITION OF THE EXISTING IMPROVEMENTS TO THE BELOW.
|  |  | Document of September 10, 2025 | Understanding | Action | Timing | Concerns | Sign off
1 |  |  | Remove all of the equipment, rooms, walls, mechanical systems and return the warehouse to base building condition as outlined in the attached Schedule "B" including but not limited to the satisfaction of all building and municipal codes, and shall have an occupancy permit from Strathcona County, which shall include the addition of any mechanical, electrical, safety, or building systems necessary for the occupancy permit to be provided which may include the addition of stairs or egress. |  |  |  |  | Active
2 |  |  | The remaining build out shall include all mechanical, electrical., and other building systems as currently in place or necessary for the operation of the remaining build out including all air handling units unless otherwise agreed to between the vendor and purchaser. |  |  |  |  | Active
3 |  |  | It is understood by both the vendor and purchaser that the purchaser will be responsible for the installation of any additional lighting to the Property. |  |  |  |  | Active
4 |  |  | The Vendor will undertake to complete the following work as part of the Vendor's work. |  |  |  |  | Active
| A |  | EXTERIOR REPAIRS |  |  |  |  | Active
|  | 1 | Repair roof flashing on southeast loading dock man door (leaking over customer entrance) |  |  |  |  | Active
|  | 2 | Inspect and repair gutter system for multiple leaks around the building |  |  |  |  | Active
|  | 3 | Install missing exterior flashing on all sides of the building. |  |  |  |  | Active
|  | 4 | Seal penetrations on exterior skins from electrical/HVAC services (open to outside) |  |  |  |  | Active
|  | 5 | Repair yellow steel railing along lower truck dock (broken and hanging) |  |  |  |  | Active
|  | 6 | Install and anchor exterior stairwell from east side corridor (near locker rooms) to lower truck dock. |  |  |  |  | Active
|  | 7 | Clean drain trough in lower dock area (exterior and interior shipping door docks) |  |  |  |  | Active
|  | 8 | Fill rock bed at northeast corner around exterior steel staircase with gravel (Stair to high for safety) |  |  |  |  | Active
| B |  | LANDSCAPING |  |  |  |  | Active
|  | 1 | Chemically control weeds in beds and non-grassed areas |  |  |  |  | Active
|  | 2 | Treat rock beds for weeds |  |  |  |  | Active
|  | 3 | Remove weeds growing in interior west and northern service corridors. |  |  |  |  | Active
| C |  | INTERIOR REPAIRS |  |  |  |  | Active
|  | 1 | Repair or replace falling/damaged insulated wrap in interior warehouse areas |  |  |  |  | Active
|  | 2 | Remove tackboard/wall coverings and prep for paint |  |  |  |  | Active
|  | 3 | Patch and prep all walls for painting |  |  |  |  | Active
|  | 4 | Seal large holes from unused service/cable penetrations |  |  |  |  | Active
|  | 5 | Inspect and reglue peeling rubber alcove base |  |  |  |  | Active
|  | 6 | Reclad west wall in warehouse container storage with drywall |  |  |  |  | Active
|  | 7 | Remove and repair screw anchors in west and east locker room corridors (from removed hooks) |  |  |  |  | Active
| D |  | PLUMBING AND UTILITIES |  |  |  |  | Active
|  | 1 | Drain underground tank |  |  |  |  | Active
|  | 2 | Fix water valves in urinals in warehouse washroom |  |  |  |  | Active
|  | 3 | Cut and cap all unused lines and pipes in general warehouse |  |  |  |  | Active
| E |  | GENERAL MAINTENANCE |  |  |  |  | Active
|  | 1 | Perform thorough general cleaning at the end of the Vendor's work including the removal of any refuse. |  |  |  |  | Active